## readme
Readme
Mandatory
1 | Do not include information that is clearly sensitive to others. This information may become widely distributed | Use generic phrases to describe initiatives IF there is a likelihood of individuals getting information that is confidential or might upset others.
2 | Do not use Excel to track projects that could be shared with others, as syncing data, and rolling up data to create reports is fraught with possible issues
3 | Use a cloud-based or server-based single source of data for tracking projects
Information
1 | Use this template as the start point for creating a communication plan
2 | Add or remove columns and rows that are relevant to your specific integrations.
3 | If you have any questions, contact your IMO for assistance
4 | All content in this document is for information only, and should not be considered a comprehensive list. By viewing or using this content you agree that Intista, its owners, employees, partners or subcontractors will not be liable for any losses or damages to your business, whether direct, indirect, consequential or other, that could result from the use of, or reference to, these materials
"Time Frame" List
Day 1
Week 1
First 30
Day 30-100
First 6 months
Year 1
Post Year 1

## Example Audiences
Example Communication Plan Template - Audiences
Stakeholder | Current level of interest (1-10) | Initial Messaging | Method(s) of communication | Release Date | Internal point of contact, or Subject Matter Expert on the stakeholder | Notes | Risks/Issues
Acquired senior management | 9 | Benefits of larger company
Acquired staff | 10 | Futures secure. No staff reduction
Staff of acquiring company | 7 | Futures secure. No staff reduction
Customers | 6 to 8 | You will continue to work with the same contact as prior to the acquisition. We intend to provide improved resources |  |  |  | Some customers are extremely important
Shareholders | 6 | Share value increased
Local press | 8 | Local business success story
Strategic Partners | 7 to 8 | You will continue to work with the same contact as prior to the acquisition. We intend to provide improved resources
Suppliers | 5 | You will continue to work with the same contact as prior to the acquisition. We intend to implement improved technology for supply chain and provide improved resources
Note on F2: A person who can provide insight into the position or behaviour of a specific stakeholder

## Example Creation
Communication Plan Template - Content Creation
Content | Media | Content Creator Responsible | Audience(s) | Message | Release Date | Notes | Risks/Issues
Welcome | PowerPoint | John Doe | Acquired senior management, all staff | Benefits of larger company
Company profile | PowerPoint | Company standard content | Staff | Futures secure. No staff reduction
Welcome video recording | Video | Jane Doe | All staff who couldn't attend the live announcement
Key partner talking points | Word document | Jane Doe | Key suppliers, partners and customers who will be informed in a face to face meeting | Opportunities for everyone after the acquisition
Customer announcement | email |  | Customers | You will continue to work with the same contact as prior to the acquisition. We intend to provide improved resources
Shareholder announcement | email |  | Shareholders | Share value increased
Press release local | Word document release to PR firm | John Doe | Local press | Local business success story
Press release wire | Word document release to PR firm | John Doe | Wired press release | Opportunity for growth
Partner announcement | email and formal letter |  | Partners and Suppliers | You will continue to work with the same contact as prior to the acquisition. We intend to provide improved resources
Social Media announcement | All social media channels | Jane Doe | Public | Great news, great prospects

## Example Delivery
Communication Plan Template - Delivery
read this note
Day | Audience | Location | Person Responsible | Media | Notes | Risks/Issues
Day 2 | Acquired senior mgt | Boston, MA | John Smith | Announcement PPT All media that will be distributed | Before Day 1. Senior mgt meeting in Manchester. Need NDAs, or similar
Day 1 | Staff | Dallas, TX | Steve Ward | Announcement PPT, staff FAQs | Town Hall meeting, lunch provided
Day 1 | Staff | Buffalo, NY | John Smith | Announcement PPT, staff FAQs | Town Hall meeting, lunch and evening dinner with mgt
Day 1 | Customer – ABC Industries | Portland, ME | Susan Williams | Press release, customer FAQs
Day 1 | Public | Websites |  | Press release | On both company websites
Day 1 | Shareholders, Customers, Local Press, Partners | (email) | John Smith | Targeted emails | Need to segment into local press and press wire
Day 2 | Staff | Austin, TX | Steve Ward | Announcement PPT, FAQs | Town Hall meeting, lunch and evening dinner with mgt
Day 3 | Staff | Chicago, IL | Barbara Jean | Announcement PPT, FAQs | Town Hall meeting, lunch provided
Note on B2: Use this sheet to prepare the Day 1 announcment of an acquisition, where each announcement is and who is delivering the announcement

## Audiences
Communication Plan Template - Audiences
Stakeholder | Current level of interest (1-10) | Initial Messaging | Method(s) of Communication | Release Date | Internal point of contact, or Subject Matter Expert on the stakeholder | Notes | Risks/Issues
Acquired senior management
Acquired staff
Staff of acquiring company
Customers
Shareholders
Local press
Strategic Partners
Suppliers
Note on F2: A person who can provide insight into the position or behaviour of a specific stakeholder

## Creation
Communication Plan Template - Content Creation
Content | Media | Content Creator Responsible | Audience(s) | Message | Release Date | Notes | Risks/Issues
Welcome
Company profile
Welcome video recording
Key partner talking points
Customer announcement
Shareholder announcement
Press release local
Press release wire
Partner announcement
Social Media announcement

## Delivery
Communication Plan Template - Delivery
read this note
Day | Audience | Location | Person Responsible | Media | Notes | Risks/Issues
Note on B2: Use this sheet to prepare the Day 1 announcment of an acquisition, where each announcement is and who is delivering the announcement